www.mjeldermanphoto.comPLANNING MEETINGS

- Exercise Planning Team

- Planning Conferences (Concept & Objectives, Initial, Mid, MSEL and Final)

Items for each conference:

  - Agenda

  - Location

  - Invitations

  - Audio/Visual

  - Registration/Sign-In

  - Food/Beverage

  - Presentation

  - Name tents/name badges

  - Facilitator

  - Note takers

  - Documentation to review (See table below)

| Concept & Objectives | Initial | Mid | MSEL | Final |
| --- | --- | --- | --- | --- |
| Budget Information Calendar/ Schedule Jurisdiction’s Hazard Assessment Previous Exercise or Real World After-Action Reports, Audits, functional assessments, etc. | Target Capabilities List (or a selection of applicable TCLs) Jurisdiction’s Hazard Assessment Previous Exercise or Real World After-Action Reports, Audits, functional assessments, etc. List of Jurisdiction Stakeholders/potential participants | Exercise Plan Draft Scenario Draft MSEL | MSEL MSEL Inject Forms Actor Cards/Scripts | Player Handbook Controller/Evaluator Handbook Simulator Handbook Exercise Evaluation Guides Simulator Handbook Final MSEL Final Exercise Plan Final Actor Cards/Scripts Draft Communications Directory |

- Objectives and Scope:

  - What hazards does your jurisdiction/organization face?

  - What geographic areas, facilities, or organizational components are most vulnerable?

  - What is the purpose of the exercise/rehearsal (i.e., objectives)?

    - What functions are most in need of rehearsal and/or improvement?

    - What Target Capabilities, Activities, and Tasks are associated with the functions in need of rehearsal/improvement?

  - What agencies and personnel are most in need of rehearsal and/or improvement?

  - Where will players participate from?

- Scenario (overview/summary or initial situation)

    - Significant Events to begin developing MSEL and Actor Cards/Scripts around.

PARTICIPANTS

- Players, Controllers, Evaluators, Simulators

  - Determine number and type

  - Invitations/Recruiting

  - Confirm exercise staff and players

  - Assign to appropriate locations/positions

- Actors

  - Determine number of actors required

  - Identify source(s) of actors

  - Confirm recruited actors

  - Develop actor waiver forms

  - Develop actor instructions

  - Identify number and type of victim actors that will be at each location/exercise site and map appropriately

  - Provide for comfort

DOCUMENTATION

- Exercise Plan (ExPlan – guides the development process by summarizing the objectives, scope, scenario, logistics, roles and responsibilities, schedule, ground rules, and communications).

- Detailed Exercise Schedule

- Master Scenario Events List

  - Major Events List

  - Detailed Events (associated with each major event)

  - Expected actions (each inject should trigger an action associated with at least one of the exercise objectives)

    - Sequence should be realistic and convincing and timed to allow the demonstration of objectives

    - On average, 3 per functional area or location per hour

    - Make injects as realistic as possible

  - Select method of simulated delivery and put each inject in the appropriate format

  - Supporting documentation, data, or visual aids (e.g., maps, patient/victim data)

  - Develop Actor Cards/Scripts in accordance with MSEL.

- Impromptu Inject Forms

- Media Injects (coordinate early if media outlets are actually producing them; ensure they correlate with the scenario and MSEL)

- Simulator Handbook (or Controller Injects) – accompany MSEL

- Controller/Evaluator Handbook

- Player Handbook (distribute in advance if possible)

- Registration/Sign-In

- Communications Directory (Identify all communications that will be used for exercise play; ensure exercise communications do not interfere with real world communications)

- Observer/Media Packets

- Exercise Evaluation Guides

  - Data Collection Aids

- Participant Critiques

  - Drop boxes/collection process

- After-Action Report/Improvement Plan

TRAININGS/BRIEFINGS

- Controller/Evaluator/Simulator Training

- Actor Training

- Player Briefing/Player Notification (e.g., no notice vs. scheduled)

  - Presentation

    - Overview of the exercise objectives

    - Organization, structure, and functionality of the exercise

    - Time period being simulated

    - Initial scenario overview

    - Ground rules and procedures

- Press Conference/Media Outreach

- Observer Briefings

- Hotwash

  - Break-out groups (if the plenary group is too large)

  - Presentation (single slide with appropriate questions)

  - Facilitator(s)

  - Easels, Pads, Markers

  - Note takers

- Controller/Evaluator Debriefing or Exercise Evaluation Conference (EEC is no longer an HSEEP element, but a very valuable activity)

- After Action Conference

LOGISTICS

- Exercise sites/venues (boundaries, security, safety)

  - Registration area

  - Assembly/staging area

  - Deployment/response route(s)

  - Observer/media area

  - Food/break areas

  - SimCell

- Safety

  - Identify Safety Controller

  - Establish and Enforce Weapons Policy

- SimCell Set Up

  - Tent Cards

  - Communications Systems

  - Access Control (Black Out)

  - Inject Tracking Board

- Resource deployment schedule

- Props and devices (e.g., debris, mannequins, flash bangs, smoke machines, pyrotechnics, etc.)

- Moulage (actual materials, staff, and location for actor moulage)

- Security/access control

- Identification

- Audio/Video

- Videotaping

- Food/beverage

- Restroom facilities

- Transportation/Shuttle Service/Parking

- Communications Technology

  - Do players have the access to technology they need?

  - Do simulators have the access to technology they need (e.g., computers, phones, radios)?

  - Do controllers/evaluators need a separate communications network?

- Signage

  - Registration

  - “This is an Exercise” reminders

  - Restricted areas (e.g., SimCell)

  - Restrooms

  - Food/Beverage Information

  - Directional

- Conduct a Site Visit, Prepare Site, and Test all Systems/Equipment

  - Conduct communications check

  - Conduct pyrotechnic and device check

  - Conduct safety check

  - Conduct weapons check